## ORÇAMENTO
PREFEITURA MUNICIPAL DE SÃO CRISTÓVÃO DO SUL - SC | [9 empty] | BDI | 1.15
PROJETO: CLUBE DE EVENTOS - PARTE 01
END.: |  | PARQUE DA FAMILIA - SÃO CRISTÓVÃO DO SUL -SC
ÁREA: |  | 171.5 | m² |  | R/m² | R/m² | 1339.6097
DATA: |  | 22/04/2012
ORÇAMENTO SIMPLIFICADO
[5 empty] | VALOR | VALOR | VALOR
ÍTEM |  | DESCRIÇÃO | UN | QTDADE | UNIT s/ BDI | UNIT C/ BDI | TOTAL | CÓDIGO | FONTE
| 1.1 | Abrigo e instalações provisórias | m² | 12 | 127.58 | 140.338 | 1684.056 | 42566 | DEINFRA
| 1.2 | Locação da obra | m² | 171.5 | 2.28 | 2.622 | 449.673 | 74077/002 | SINAPI
| 1.3 | Placa de obra | m² | 3 | 222.17 | 255.4955 | 766.4865 | 74209/001 | SINAPI
| 1.4 | Projeto estrutural | m² | 171.5 | 8.97 | 9.867 | 1692.1905 | 42513 | DEINFRA
| 1.5 | Projeto de fundações | m² | 171.5 | 2.68 | 2.948 | 505.582 | 42514 | DEINFRA
| 1.6 | Projeto Hidrossanitário | m² | 171.5 | 4.48 | 4.928 | 845.152 | 42515 | DEINFRA
| 1.7 | Projeto de instalações elétricas | m² | 171.5 | 4.48 | 4.928 | 845.152 | 42512 | DEINFRA
| 1.8 | Projeto Preventivo contra-incêndio | m² | 171.5 | 4.48 | 4.928 | 845.152 | 42516 | DEINFRA
SERVIÇOS PRELIMINARES | [6 empty] | 7633.444
| 2.1 | Escavação mecânica de solo prof até 1,50 m | m³ | 53.04 | 4.01 | 4.6115 | 244.594 | 73962/013 | SINAPI
| 2.2 | Escavação manual de solo prof até 1,50 m | m³ | 14.47 | 25.18 | 28.957 | 419.0078 | 73965/010 | SINAPI
| 2.3 | Lastro de concreto magro | m³ | 0.9 | 248.94 | 286.281 | 257.6529 | 6042 | SINAPI
| 2.4 | Sapatas de concreto armado fck 25 Mpa | m³ | 5.39 | 1173.91 | 1349.9965 | 7276.4811 | 6501 | SINAPI
| 2.5 | Colarinhos de concreto armado fck 25 Mpa c/ caixaria e escoramento | m³ | 1.84 | 1173.91 | 1349.9965 | 2483.9936 | 6501 | SINAPI
| 2.6 | Reaterro de fundações | m³ | 30.44 | 21.58 | 24.817 | 755.4295 | 73964/006 | SINAPI
| 2.7 | Vigas de baldrame de concreto armado fck 25Mpa c/ caixaria e escoramento | m³ | 7.23 | 1173.91 | 1349.9965 | 9760.4747 | 6501 | SINAPI
| 2.8 | Impermeabilização de baldrames - 2 demãos | m² | 72.35 | 5.76 | 6.624 | 479.2464 | 74106/001 | SINAPI
INFRA ESTRUTURA | [6 empty] | 21676.8799
| 3.1 | Pilares de concreto armado fck 25 Mpa com caixaria e escoramento | m³ | 3.78 | 1173.91 | 1349.9965 | 5102.9868 | 6501 | SINAPI
| 3.2 | Vigas de concreto armado fck 25 Mpa com caixaria e escoramento | m³ | 7.23 | 1173.91 | 1349.9965 | 9760.4747 | 6501 | SINAPI
| 3.3 | Laje pré-fabricada piso cx d'água - esp.=12cm | m² | 14.01 | 57.04 | 65.596 | 919 | 74202/002 | SINAPI
| 3.4 | Laje pré-fabricada cobertura cx d'água - esp.=12cm | m² | 14.01 | 49.88 | 57.362 | 803.6416 | 74202/001 | SINAPI
| 3.5 | Impermeabilização com manta - laje caixa d'água | m² | 14.01 | 50.15 | 57.6725 | 807.9917 | 73762/001 | SINAPI
SUPERESTRUTURA | [6 empty] | 17394.0948
| 4.1 | Alvenaria de tijolos 6 furos (10x15x20) | m² | 512.94 | 38.48 | 44.252 | 22698.6209 | 73935/005 | SINAPI
| 4.2 | Divisória granito | m² | 31.92 | 251.93 | 289.7195 | 9247.8464 | 72244 | SINAPI
| 4.3 | Vergas e contravergas de concreto armado | m³ | 1.1 | 965.61 | 1110.4515 | 1221.4967 | 74099/001 | SINAPI
| 4.4 | Cintas em concreto armado - platibanda | m³ | 0.42 | 965.61 | 1110.4515 | 466.3896 | 74099/001 | SINAPI
PAREDES E PAINÉIS | [6 empty] | 33634.3536
| 5.1 | Estrutura de madeira para cobertura fibrocimento 6mm | m² | 157.49 | 42.91 | 49.3465 | 7771.5803 | 72081 | SINAPI
| 5.2 | Manta para isolamento térmico | m² | 157.49 | 57.68 | 66.332 | 10446.6267 | 73833/001 | SINAPI
| 5.3 | Cobertura telha fibrocimento - 6mm | m² | 157.49 | 20.8 | 23.92 | 3767.1608 | 74088/001 | SINAPI
| 5.4 | Calhas galvanizadas - n°. 24 desenvolvimento 33 | m | 38.9 | 21.37 | 24.5755 | 955.9869 | 72104 | SINAPI
| 5.5 | Rufo galvanizado interno a platibanda | m | 71.2 | 13.63 | 15.6745 | 1116.0244 | 72106 | SINAPI
| 5.6 | Rufo galvanizado sobre a platibanda | m | 71.2 | 13.63 | 15.6745 | 1116.0244 | 72106 | SINAPI
| 5.7 | Condutor PVC - 100 mm - incl. Conexões e fixadores | m | 36 | 14.37 | 16.5255 | 594.918 | 74026/001 | SINAPI
| 5.8 | Caixa de passagem c/ inspeção 40x40x40cm | un | 9 | 59.2 | 68.08 | 612.72 | 74248/001 | SINAPI
COBERTURA | [6 empty] | 26381.0415
| 6.1 | Chapisco | m² | 1065.88 | 3.44 | 3.956 | 4216.6213 | 73928/001 | SINAPI
| 6.2 | Emboço | m² | 1065.88 | 14.95 | 17.1925 | 18325.1419 | 5978 | SINAPI
| 6.3 | Reboco | m² | 150.96 | 10.48 | 12.052 | 1819.3699 | 5995 | SINAPI
| 6.4 | Azulejos comuns 43x43cm PEI-4 | m² | 452.24 | 20.24 | 23.276 | 10526.3382 | 73912/001 | SINAPI
REVESTIMENTO DE PAREDES | [6 empty] | 34887.4713
| 7.1 | Forro PVC em placas com largura de 10cm esp. 8mm comp. 6m c/ tarugamento | m² | 154.71 | 30 | 34.5 | 5337.495 | 41602 | SINAPI
FORROS | [6 empty] | 5337.495
| 8.1 | Instalação de água fria completa, com tubos, conexões e acessórios | pt | 27 | 57.02 | 65.573 | 1770.471 | 73959/002 | SINAPI
| 8.2 | Registro de gaveta metálico 2" | un | 1 | 95.54 | 109.871 | 109.871 | 74181/001 | SINAPI
| 8.3 | Registro de gaveta metálico 1" | un | 1 | 72.48 | 83.352 | 83.352 | 74175/001 | SINAPI
| 8.4 | Registro gaveta 50mm | un | 5 | 95.54 | 109.871 | 549.355 | 74181/001 | SINAPI
| 8.5 | Registro gaveta 25mm | un | 5 | 72.48 | 83.352 | 416.76 | 74175/001 | SINAPI
| 8.6 | Valvula para vaso sanitário - completa base e acabamento | un | 8 | 151.9 | 174.685 | 1397.48 | 40729 | SINAPI
| 8.7 | Assento plástico para vaso sanitário s/ abertura frontal | un | 8 | 14.06 | 16.169 | 129.352 | 74230/001 | SINAPI
| 8.8 | Vaso sanitário | un | 8 | 141.02 | 162.173 | 1297.384 | 6021 | SINAPI
| 8.9 | Mictório cerâmico | un | 3 | 181.05 | 208.2075 | 624.6225 | 73947/005 | SINAPI
| 8.10 | Porta papel higiênico | un | 8 | 37.46 | 37.46 | 299.68 | 11703 (SINAPI ins) | DEINFRA
| 8.11 | Porta papel toalha | un | 7 | 79.45 | 79.45 | 556.15 | 43808 (DEINFRA) | DEINFRA
| 8.12 | Porta sabonete líquido | un | 7 | 22.85 | 26.2775 | 183.9425 | 73947/012 | SINAPI
| 8.13 | Lavatório de mãos de louça branco com coluna e sifão | un | 7 | 214.29 | 246.4335 | 1725.0345 | 73947/002 | SINAPI
| 8.14 | Torneira de lavatório metálica cromada - com fechamento automático | un | 7 | 304.84 | 304.84 | 2133.88 | 43714 | DEINFRA
| 8.15 | Torneira de pia metálica para cozinha | un | 4 | 218.56 | 218.56 | 874.24 | 42952 | DEINFRA
| 8.16 | Cuba em aço inox | un | 8 | 281.12 | 281.12 | 2248.96 | 42909 | DEINFRA
| 8.17 | Instalação de esgoto completa, com tubos, conexões e acessórios | un | 27 | 71.87 | 82.6505 | 2231.5635 | 73958/001 | SINAPI
| 8.18 | Fossa séptica conforme norma - NBR 7229 | m³ | 2.26 | 526.61 | 526.61 | 1190.1386 | 43154 (DEINFRA) | DEINFRA
| 8.19 | Filtro anaeróbio conforme norma - NBR 13969 | m³ | 1.59 | 558.98 | 558.98 | 888.7782 | 43153 (DEINFRA) | DEINFRA
| 8.20 | Caixa de passagem c/ inspeção 40x40x40cm | un | 9 | 59.2 | 68.08 | 612.72 | 74248/001 | SINAPI
| 8.21 | Caixa de gordura 60x60x60 | un | 3 | 146.6 | 168.59 | 505.77 | 74051/001 | SINAPI
| 8.22 | Reservatório de fibra capacidade 500 litros | un | 1 | 334.55 | 384.7325 | 384.7325 | 73735/002 | SINAPI
INSTALAÇÕES HIDRO-SANITÁRIAS | [6 empty] | 20214.2373
| 9.1 | Caixa para medidor trifásico (Medidor Eletrônico) | pç | 1 | 163.23 | 187.7145 | 187.7145 | 74247/001 | SINAPI
| 9.2 | Disjuntor termomagnético monofásico 10A | pç | 10 | 8.4 | 9.66 | 96.6 | 74130/001 | SINAPI
| 9.3 | Disjuntor termomagnético monofásico 40A | pç | 1 | 47.7 | 54.855 | 54.855 | 74130/003 | SINAPI
| 9.4 | Instações elétricas - incluindo eletrodutos, conexões, fios, cabos e caixas- diversas bitolas | un. | 65 | 89.74 | 103.201 | 6708.065 | 74054/001 | SINAPI
| 9.5 | Quadro de embutir para 12 disjuntores monofásicos | pç | 1 | 88.91 | 102.2465 | 102.2465 | 74131/003 | SINAPI
| 9.6 | Luminária de sobrepor para 2 lâmpadas flour. 20W, completa | pç | 16 | 66.17 | 76.0955 | 1217.528 | 73953/002 | SINAPI
| 9.7 | Luminária de sobrepor para 2 lâmpadas flour. 40W, completa | pç | 17 | 71.62 | 82.363 | 1400.171 | 73953/006 | SINAPI
| 9.8 | Luminária tipo projetor - lampada vapor metálico 250W | pç | 4 | 104.62 | 120.313 | 481.252 | 72281+73831/002 | SINAPI | 82.62 | 22
| 9.9 | Tomada de embutir 2P+T (eletrodutos, e caixas) | pç | 20 | 61.03 | 70.1845 | 1403.69 | 73917/003 | SINAPI
| 9.10 | Interruptor de embutir simples - 01 seção | pç | 16 | 7.61 | 8.7515 | 140.024 | 72331 | SINAPI
| 9.11 | Interruptor de embutir simples - 02 seções | pç | 6 | 10.22 | 11.753 | 70.518 | 72332 | SINAPI
| 9.12 | Interruptor de embutir simples - 03 seções | pç | 2 | 10.22 | 11.753 | 23.506 | 72332 | SINAPI
| 9.13 | Interruptor de embutir simples - 01 seção - paralelo | pç | 2 | 10.22 | 11.753 | 23.506 | 72332 | SINAPI
| 9.14 | Interruptor de embutir simples - 02 seções - paralelo | pç | 2 | 10.22 | 11.753 | 23.506 | 72332 | SINAPI
| 9.15 | Entrada de energia trifásica, completa com poste, amarração, isolador, fios | un. | 1 | 823.56 | 823.56 | 823.56 | 43524 | DEINFRA
| 9.16 | Tampa de Ferro Fundido p/caixa subterrânea 71x47cm | pç | 1 | 152.01 | 174.8115 | 174.8115 | 40678 | SINAPI
INSTALAÇÕES ELÉTRICAS | [6 empty] | 12931.5535
| 10.1 | Lastro de brita nº. 1 - piso | m³ | 10.62 | 93.14 | 107.111 | 1137.5188 | 74164/004 | SINAPI
| 10.2 | Lona plástica preta (piso) | m² | 212.25 | 2.84 | 3.266 | 693.2085 | 68053 | SINAPI
| 10.3 | Piso concreto 6cm | m³ | 12.74 | 248.94 | 286.281 | 3647.2199 | 6042 | SINAPI
| 10.4 | Contrapiso para bases coladas | m² | 154.71 | 17.81 | 20.4815 | 3168.6929 | 73919/008 | SINAPI
| 10.5 | Pavim.ceramica 43x43 antiderrapante PEI-4 colada | m² | 154.71 | 21.36 | 24.564 | 3800.2964 | 73946/001 | SINAPI
| 10.6 | Rodapé de cerâmica 7 cm de altura c/ argamassa colante | m | 55.43 | 7.87 | 9.0505 | 501.6692 | 73985/001 | SINAPI
PISOS E PAVIMENTAÇÕES | [6 empty] | 12948.6058
| 11.1 | Janela de vidro - J1- correr (3,00 x 0,60m) - c/ ferragens | m² | 9 | 111.72 | 128.478 | 1156.302 | 72118 | SINAPI
| 11.2 | Janela de vidro - J2- maxim-ar (0,80 x 0,60m) - c/ ferragens | m² | 1.92 | 111.72 | 128.478 | 246.6778 | 72118 | SINAPI
| 11.3 | Porta/Janela de vidro temperado 10mm - PJ1- correr 4fls. (4,00 x 2,50m) - c/ ferragens | m² | 20 | 230.5 | 230.5 | 4610 |  | MERCADO
| 11.4 | Porta de alumínio - P1 - veneziana abrir (0,80x2,10m) - c/ ferragens | m² | 13.44 | 385.03 | 442.7845 | 5951.0237 | 74071/002 | SINAPI
| 11.5 | Porta de alumínio - P2 - veneziana abrir (0,70x2,10m) - c/ ferragens | m² | 2.94 | 385.03 | 442.7845 | 1301.7864 | 74071/002 | SINAPI
| 11.6 | Porta de alumínio - P3 - veneziana abrir (0,90x2,10m) - c/ ferragens | m² | 1.89 | 385.03 | 442.7845 | 836.8627 | 74071/002 | SINAPI
ESQUADRIAS E FERRAGENS | [6 empty] | 14102.6526
| 12.1 | Selador sobre alvenaria | m² | 556.19 | 3.69 | 4.2435 | 2360.1923 | 74233/001 | SINAPI
| 12.2 | Pintura em alvenaria com tinta acrílica 2 demãos - interna e externa c/ textura | m² | 476.54 | 12.4 | 14.26 | 6795.4604 | 73746/001 | SINAPI
PINTURA | [6 empty] | 9155.6527
| 13.1 | Soleiras e peitoris em granito | m | 24 | 53.22 | 61.203 | 1468.872 | 74111/001 | SINAPI
| 13.2 | Tela de proteção contra vetores | m² | 3.6 | 150 | 150 | 540
| 13.3 | Bancada em granito | m | 9.53 | 179.21 | 206.0915 | 1964.052 | 74126/001 | SINAPI
| 13.4 | Tubulação em cobre | m | 18 | 15.26 | 17.549 | 315.882 | 74061/001 | SINAPI
| 13.5 | Central de Gás | un | 1 | 750 | 750 | 750 |  | MERCADO
| 13.6 | Conjunto de 3 barras de apoio metálicas cromadas p/ BWC PNE | cj | 1 | 332.4 | 332.4 | 332.4 | 47980 | DEINFRA
| 13.7 | Pergolado em madeira - impermeabilizado | m³ | 1.43 | 4850 | 4850 | 6935.5 |  | MERCADO
COMPLEMENTOS | [6 empty] | 12306.706
| 14.1 | Extintor PQS - 6kg - com placas indicativas e instalado conforme normas | un | 1 | 93.71 | 107.7665 | 107.7665 | 73775/001 | SINAPI
| 14.2 | Luminária de emergência - fluorescente com inscrição "SAÍDA" - Tipo A | un | 2 | 202.06 | 202.06 | 404.12 | 43730 | DEINFRA
| 14.3 | Luminária de emergência - fluorescente com inscrição "SAÍDA" - Tipo B | un | 2 | 202.06 | 202.06 | 404.12 | 43731 | DEINFRA
PREVENTIVO CONTRA INCÊNDIO | [6 empty] | 916.0065
| 15.1 | Retirada de entulhos e limpeza final da obra | m² | 171.5 | 1.13 | 1.2995 | 222.8642 | 9537 | SINAPI
SERVIÇOS FINAIS | [6 empty] | 222.8642
TOTAL | [6 empty] | 229743.0587
*BDI utilizado 20% - Tabela base SINAPI Março 2012 e DEINFRA Agosto 2011 - corrigido

## CRONOGRAMA
PREFEITURA MUNICIPAL DE SÃO CRISTÓVÃO DO SUL - SC
PROJETO: CLUBE DE EVENTOS - PARTE 01
END.: |  | PARQUE DA FAMILIA - SÃO CRISTÓVÃO DO SUL -SC
ÁREA: |  | 171.5
DATA: |  | 22/04/2012 |  |  |  |  | CRONOGRAMA FÍSICO FINANCEIRO
[7 empty] | 1º MÊS | [5 empty] | 2º MÊS | [5 empty] | 3º MÊS | [5 empty] | 4º MÊS | [5 empty] | 5º MÊS
[5 empty] | VALOR | VALOR | MATERIAL | VALOR | % | MATERIAL | VALOR | % | MATERIAL | VALOR | % | MATERIAL | VALOR | % | MATERIAL | VALOR | % | MATERIAL | VALOR | % | MATERIAL | VALOR | % | MATERIAL | VALOR | % | MATERIAL | VALOR | % | MATERIAL | VALOR | %
ÍTEM |  | DESCRIÇÃO | UN | QTDADE | UNIT s/ BDI | TOTAL | PERÍODO |  |  | ACUMULADO |  |  | PERÍODO |  |  | ACUMULADO |  |  | PERÍODO |  |  | ACUMULADO |  |  | PERÍODO |  |  | ACUMULADO |  |  | PERÍODO |  |  | ACUMULADO
| 1.1 | Abrigo e instalações provisórias | m² | 12 | 140.338 | 1684.056 | 12 | 1684.056 | 100% |  | 1684.056 | 100% |  | 0 | 0% | 12 | 1684.056 | 100% |  | 0 | 0% | 12 | 1684.056 | 100% |  | 0 | 0% | 12 | 1684.056 | 100% |  | 0 | 0% | 12 | 1684.056 | 100% | 100% | 0
| 1.2 | Locação da obra | m² | 171.5 | 2.622 | 449.673 | 171.5 | 449.673 | 100% |  | 449.673 | 100% |  | 0 | 0% | 171.5 | 449.673 | 100% |  | 0 | 0% | 171.5 | 449.673 | 100% |  | 0 | 0% | 171.5 | 449.673 | 100% |  | 0 | 0% | 171.5 | 449.673 | 100% | 100% | 0
| 1.3 | Placa de obra | m² | 3 | 255.4955 | 766.4865 | 3 | 766.4865 | 100% |  | 766.4865 | 100% |  | 0 | 0% | 3 | 766.4865 | 100% |  | 0 | 0% | 3 | 766.4865 | 100% |  | 0 | 0% | 3 | 766.4865 | 100% |  | 0 | 0% | 3 | 766.4865 | 100% | 100% | 0
| 1.4 | Projeto estrutural | m² | 171.5 | 9.867 | 1692.1905 | 171.5 | 1692.1905 | 100% |  | 1692.1905 | 100% |  | 0 | 0% | 171.5 | 1692.1905 | 100% |  | 0 | 0% | 171.5 | 1692.1905 | 100% |  | 0 | 0% | 171.5 | 1692.1905 | 100% |  | 0 | 0% | 171.5 | 1692.1905 | 100% | 100% | 0
| 1.5 | Projeto de fundações | m² | 171.5 | 2.948 | 505.582 | 171.5 | 505.582 | 100% |  | 505.582 | 100% |  | 0 | 0% | 171.5 | 505.582 | 100% |  | 0 | 0% | 171.5 | 505.582 | 100% |  | 0 | 0% | 171.5 | 505.582 | 100% |  | 0 | 0% | 171.5 | 505.582 | 100% | 100% | 0
| 1.6 | Projeto Hidrossanitário | m² | 171.5 | 4.928 | 845.152 | 171.5 | 845.152 | 100% |  | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% | 100% | 0
| 1.7 | Projeto de instalações elétricas | m² | 171.5 | 4.928 | 845.152 | 171.5 | 845.152 | 100% |  | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% | 100% | 0
| 1.8 | Projeto Preventivo contra-incêndio | m² | 171.5 | 4.928 | 845.152 | 171.5 | 845.152 | 100% |  | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% |  | 0 | 0% | 171.5 | 845.152 | 100% | 100% | 0
SERVIÇOS PRELIMINARES | [5 empty] | 7633.444 |  | 7633.444 | 100% |  | 7633.444 | 100% |  | 0 | 0% |  | 7633.444 | 100% |  | 0 | 0% |  | 7633.444 | 100% |  | 0 | 0% |  | 7633.444 | 100% |  | 0 | 0% |  | 7633.444 | 100% |  | 0
| 2.1 | Escavação mecânica de solo prof até 1,50 m | m³ | 53.04 | 4.6115 | 244.594 | 53.04 | 244.594 | 100% |  | 244.594 | 100% |  | 0 | 0% | 53.04 | 244.594 | 100% |  | 0 | 0% | 53.04 | 244.594 | 100% |  | 0 | 0% | 53.04 | 244.594 | 100% |  | 0 | 0% | 53.04 | 244.594 | 100% | 100% | 0
| 2.2 | Escavação manual de solo prof até 1,50 m | m³ | 14.47 | 28.957 | 419.0078 | 14.47 | 419.0078 | 100% |  | 419.0078 | 100% |  | 0 | 0% | 14.47 | 419.0078 | 100% |  | 0 | 0% | 14.47 | 419.0078 | 100% |  | 0 | 0% | 14.47 | 419.0078 | 100% |  | 0 | 0% | 14.47 | 419.0078 | 100% | 100% | 0
| 2.3 | Lastro de concreto magro | m³ | 0.9 | 286.281 | 257.6529 | 0.9 | 257.6529 | 100% |  | 257.6529 | 100% |  | 0 | 0% | 0.9 | 257.6529 | 100% |  | 0 | 0% | 0.9 | 257.6529 | 100% |  | 0 | 0% | 0.9 | 257.6529 | 100% |  | 0 | 0% | 0.9 | 257.6529 | 100% | 100% | 0
| 2.4 | Sapatas de concreto armado fck 25 Mpa | m³ | 5.39 | 1349.9965 | 7276.4811 | 5.39 | 7276.4811 | 100% |  | 7276.4811 | 100% |  | 0 | 0% | 5.39 | 7276.4811 | 100% |  | 0 | 0% | 5.39 | 7276.4811 | 100% |  | 0 | 0% | 5.39 | 7276.4811 | 100% |  | 0 | 0% | 5.39 | 7276.4811 | 100% | 100% | 0
| 2.5 | Colarinhos de concreto armado fck 25 Mpa c/ caixaria e escoramento | m³ | 1.84 | 1349.9965 | 2483.9936 | 1.84 | 2483.9936 | 100% |  | 2483.9936 | 100% |  | 0 | 0% | 1.84 | 2483.9936 | 100% |  | 0 | 0% | 1.84 | 2483.9936 | 100% |  | 0 | 0% | 1.84 | 2483.9936 | 100% |  | 0 | 0% | 1.84 | 2483.9936 | 100% | 100% | 0
| 2.6 | Reaterro de fundações | m³ | 30.44 | 24.817 | 755.4295 | 30.44 | 755.4295 | 100% |  | 755.4295 | 100% |  | 0 | 0% | 30.44 | 755.4295 | 100% |  | 0 | 0% | 30.44 | 755.4295 | 100% |  | 0 | 0% | 30.44 | 755.4295 | 100% |  | 0 | 0% | 30.44 | 755.4295 | 100% | 100% | 0
| 2.7 | Vigas de baldrame de concreto armado fck 25Mpa c/ caixaria e escoramento | m³ | 7.23 | 1349.9965 | 9760.4747 | 7.23 | 9760.4747 | 100% |  | 9760.4747 | 100% |  | 0 | 0% | 7.23 | 9760.4747 | 100% |  | 0 | 0% | 7.23 | 9760.4747 | 100% |  | 0 | 0% | 7.23 | 9760.4747 | 100% |  | 0 | 0% | 7.23 | 9760.4747 | 100% | 100% | 0
| 2.8 | Impermeabilização de baldrames - 2 demãos | m² | 72.35 | 6.624 | 479.2464 | 72.35 | 479.2464 | 100% |  | 479.2464 | 100% |  | 0 | 0% | 72.35 | 479.2464 | 100% |  | 0 | 0% | 72.35 | 479.2464 | 100% |  | 0 | 0% | 72.35 | 479.2464 | 100% |  | 0 | 0% | 72.35 | 479.2464 | 100% | 100% | 0
INFRA ESTRUTURA | [5 empty] | 21676.8799 |  | 21676.8799 | 100% |  | 21676.8799 | 100% |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0
0
| 3.1 | Pilares de concreto armado fck 25 Mpa com caixaria e escoramento | m³ | 3.78 | 1349.9965 | 5102.9868 |  | 0 | 0% |  | 0 | 0% | 3.78 | 5102.9868 | 100% | 3.78 | 5102.9868 | 100% |  | 0 | 0% | 3.78 | 5102.9868 | 100% |  | 0 | 0% | 3.78 | 5102.9868 | 100% |  | 0 | 0% | 3.78 | 5102.9868 | 100% | 100% | 0
| 3.2 | Vigas de concreto armado fck 25 Mpa com caixaria e escoramento | m³ | 7.23 | 1349.9965 | 9760.4747 |  | 0 | 0% |  | 0 | 0% | 7.23 | 9760.4747 | 100% | 7.23 | 9760.4747 | 100% |  | 0 | 0% | 7.23 | 9760.4747 | 100% |  | 0 | 0% | 7.23 | 9760.4747 | 100% |  | 0 | 0% | 7.23 | 9760.4747 | 100% | 100% | 0
| 3.3 | Laje pré-fabricada piso cx d'água - esp.=12cm | m² | 14.01 | 65.596 | 919 |  | 0 | 0% |  | 0 | 0% | 14.01 | 919 | 100% | 14.01 | 919 | 100% |  | 0 | 0% | 14.01 | 919 | 100% |  | 0 | 0% | 14.01 | 919 | 100% |  | 0 | 0% | 14.01 | 919 | 100% | 100% | 0
| 3.4 | Laje pré-fabricada cobertura cx d'água - esp.=12cm | m² | 14.01 | 57.362 | 803.6416 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 14.01 | 803.6416 | 100% | 14.01 | 803.6416 | 100% |  | 0 | 0% | 14.01 | 803.6416 | 100% |  | 0 | 0% | 14.01 | 803.6416 | 100% | 100% | 0
| 3.5 | Impermeabilização com manta - laje caixa d'água | m² | 14.01 | 57.6725 | 807.9917 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 14.01 | 807.9917 | 100% | 14.01 | 807.9917 | 100% |  | 0 | 0% | 14.01 | 807.9917 | 100% |  | 0 | 0% | 14.01 | 807.9917 | 100% | 100% | 0
SUPERESTRUTURA | [5 empty] | 17394.0948 |  | 0 | 0% |  | 0 | 0% |  | 15782.4614 | 90.73% |  |  |  |  | 1611.6333 | 9.265% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0
0
| 4.1 | Alvenaria de tijolos 6 furos (10x15x20) | m² | 512.94 | 44.252 | 22698.6209 |  | 0 | 0% |  | 0 | 0% | 400 | 17700.8 | 77.98% | 400 | 17700.8 | 77.98% | 112.94 | 4997.8209 | 22.02% | 512.94 | 22698.6209 | 100% |  | 0 | 0% | 512.94 | 22698.6209 | 100% |  | 0 | 0% | 512.94 | 22698.6209 | 100% | 100% | 0
| 4.2 | Divisória granito | m² | 31.92 | 289.7195 | 9247.8464 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 31.92 | 9247.8464 | 100% | 31.92 | 9247.8464 | 100% | 100% | 0
| 4.3 | Vergas e contravergas de concreto armado | m³ | 1.1 | 1110.4515 | 1221.4967 |  | 0 | 0% |  | 0 | 0% | 1.1 | 1221.4967 | 100% | 1.1 | 1221.4967 | 100% |  | 0 | 0% | 1.1 | 1221.4967 | 100% |  | 0 | 0% | 1.1 | 1221.4967 | 100% |  | 0 | 0% | 1.1 | 1221.4967 | 100% | 100% | 0
| 4.4 | Cintas em concreto armado - platibanda | m³ | 0.42 | 1110.4515 | 466.3896 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 0.42 | 466.3896 | 100% | 0.42 | 466.3896 | 100% |  | 0 | 0% | 0.42 | 466.3896 | 100% |  | 0 | 0% | 0.42 | 466.3896 | 100% | 100% | 0
PAREDES E PAINÉIS | [5 empty] | 33634.3536 |  | 0 | 0% |  |  |  |  | 18922.2967 | 56.26% |  |  |  |  | 5464.2105 | 16.25% |  |  |  |  | 0 | 0% |  |  |  |  | 9247.8464 | 27.5% |  |  |  |  | 0
0
| 5.1 | Estrutura de madeira para cobertura fibrocimento 6mm | m² | 157.49 | 49.3465 | 7771.5803 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 157.49 | 7771.5803 | 100% | 157.49 | 7771.5803 | 100% |  | 0 | 0% | 157.49 | 7771.5803 | 100% |  | 0 | 0% | 157.49 | 7771.5803 | 100% | 100% | 0
| 5.2 | Manta para isolamento térmico | m² | 157.49 | 66.332 | 10446.6267 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 157.49 | 10446.6267 | 100% | 157.49 | 10446.6267 | 100% |  | 0 | 0% | 157.49 | 10446.6267 | 100% |  | 0 | 0% | 157.49 | 10446.6267 | 100% | 100% | 0
| 5.3 | Cobertura telha fibrocimento - 6mm | m² | 157.49 | 23.92 | 3767.1608 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 157.49 | 3767.1608 | 100% | 157.49 | 3767.1608 | 100% |  | 0 | 0% | 157.49 | 3767.1608 | 100% |  | 0 | 0% | 157.49 | 3767.1608 | 100% | 100% | 0
| 5.4 | Calhas galvanizadas - n°. 24 desenvolvimento 33 | m | 38.9 | 24.5755 | 955.9869 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 38.9 | 955.9869 | 100% | 38.9 | 955.9869 | 100% |  | 0 | 0% | 38.9 | 955.9869 | 100% |  | 0 | 0% | 38.9 | 955.9869 | 100% | 100% | 0
| 5.5 | Rufo galvanizado interno a platibanda | m | 71.2 | 15.6745 | 1116.0244 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 71.2 | 1116.0244 | 100% | 71.2 | 1116.0244 | 100% |  | 0 | 0% | 71.2 | 1116.0244 | 100% |  | 0 | 0% | 71.2 | 1116.0244 | 100% | 100% | 0
| 5.6 | Rufo galvanizado sobre a platibanda | m | 71.2 | 15.6745 | 1116.0244 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 71.2 | 1116.0244 | 100% | 71.2 | 1116.0244 | 100% |  | 0 | 0% | 71.2 | 1116.0244 | 100% |  | 0 | 0% | 71.2 | 1116.0244 | 100% | 100% | 0
| 5.7 | Condutor PVC - 100 mm - incl. Conexões e fixadores | m | 36 | 16.5255 | 594.918 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 36 | 594.918 | 100% | 36 | 594.918 | 100% |  | 0 | 0% | 36 | 594.918 | 100% |  | 0 | 0% | 36 | 594.918 | 100% | 100% | 0
| 5.8 | Caixa de passagem c/ inspeção 40x40x40cm | un | 9 | 68.08 | 612.72 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 9 | 612.72 | 100% | 9 | 612.72 | 100% |  | 0 | 0% | 9 | 612.72 | 100% |  | 0 | 0% | 9 | 612.72 | 100% | 100% | 0
COBERTURA | [5 empty] | 26381.0415 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  |  |  |  | 26381.0415 | 100% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0
0
| 6.1 | Chapisco | m² | 1065.88 | 3.956 | 4216.6213 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 865.88 | 3425.4213 | 81.24% | 865.88 | 3425.4213 | 81.24% | 200 | 791.2 | 18.76% | 1065.88 | 4216.6213 | 100% |  | 0 | 0% | 1065.88 | 4216.6213 | 100% | 100% | 0
| 6.2 | Emboço | m² | 1065.88 | 17.1925 | 18325.1419 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 865.88 | 14886.6419 | 81.24% | 865.88 | 14886.6419 | 81.24% | 200 | 3438.5 | 18.76% | 1065.88 | 18325.1419 | 100% |  | 0 | 0% | 1065.88 | 18325.1419 | 100% | 100% | 0
| 6.3 | Reboco | m² | 150.96 | 12.052 | 1819.3699 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 150.96 | 1819.3699 | 100% | 150.96 | 1819.3699 | 100% |  | 0 | 0% | 150.96 | 1819.3699 | 100% | 100% | 0
| 6.4 | Azulejos comuns 43x43cm PEI-4 | m² | 452.24 | 23.276 | 10526.3382 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 252.24 | 5871.1382 | 55.78% | 252.24 | 5871.1382 | 55.78% | 200 | 4655.2 | 44.22% | 452.24 | 10526.3382 | 100% | 100% | 0
REVESTIMENTO DE PAREDES | [5 empty] | 34887.4713 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  |  |  |  | 18312.0632 | 52.49% |  |  |  |  | 11920.2082 | 34.17% |  |  |  |  | 4655.2 | 13.34% |  |  |  |  | 0
0
| 7.1 | Forro PVC em placas com largura de 10cm esp. 8mm comp. 6m c/ tarugamento | m² | 154.71 | 34.5 | 5337.495 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 154.71 | 5337.495 | 100% | 154.71 | 5337.495 | 100% | 100% | 0
FORROS | [5 empty] | 5337.495 |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 5337.495 | 100% |  |  |  |  | 0
0
| 8.1 | Instalação de água fria completa, com tubos, conexões e acessórios | pt | 27 | 65.573 | 1770.471 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 27 | 1770.471 | 100% | 27 | 1770.471 | 100% |  | 0 | 0% | 27 | 1770.471 | 100% |  | 0 | 0% | 27 | 1770.471 | 100% | 100% | 0
| 8.2 | Registro de gaveta metálico 2" | un | 1 | 109.871 | 109.871 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 109.871 | 100% | 1 | 109.871 | 100% |  | 0 | 0% | 1 | 109.871 | 100% |  | 0 | 0% | 1 | 109.871 | 100% | 100% | 0
| 8.3 | Registro de gaveta metálico 1" | un | 1 | 83.352 | 83.352 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 83.352 | 100% | 1 | 83.352 | 100% |  | 0 | 0% | 1 | 83.352 | 100% |  | 0 | 0% | 1 | 83.352 | 100% | 100% | 0
| 8.4 | Registro gaveta 50mm | un | 5 | 109.871 | 549.355 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 5 | 549.355 | 100% | 5 | 549.355 | 100% |  | 0 | 0% | 5 | 549.355 | 100% |  | 0 | 0% | 5 | 549.355 | 100% | 100% | 0
| 8.5 | Registro gaveta 25mm | un | 5 | 83.352 | 416.76 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 5 | 416.76 | 100% | 5 | 416.76 | 100% |  | 0 | 0% | 5 | 416.76 | 100% |  | 0 | 0% | 5 | 416.76 | 100% | 100% | 0
| 8.6 | Valvula para vaso sanitário - completa base e acabamento | un | 8 | 174.685 | 1397.48 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 8 | 1397.48 | 100% | 8 | 1397.48 | 100% | 100% | 0
| 8.7 | Assento plástico para vaso sanitário s/ abertura frontal | un | 8 | 16.169 | 129.352 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 8 | 129.352 | 100% | 8 | 129.352 | 100% | 100% | 0
| 8.8 | Vaso sanitário | un | 8 | 162.173 | 1297.384 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 8 | 1297.384 | 100% | 8 | 1297.384 | 100% | 100% | 0
| 8.9 | Mictório cerâmico | un | 3 | 208.2075 | 624.6225 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 3 | 624.6225 | 100% | 3 | 624.6225 | 100% | 100% | 0
| 8.10 | Porta papel higiênico | un | 8 | 37.46 | 299.68 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 8 | 299.68 | 100% | 8 | 299.68 | 100% | 100% | 0
| 8.11 | Porta papel toalha | un | 7 | 79.45 | 556.15 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 7 | 556.15 | 100% | 7 | 556.15 | 100% | 100% | 0
| 8.12 | Porta sabonete líquido | un | 7 | 26.2775 | 183.9425 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 7 | 183.9425 | 100% | 7 | 183.9425 | 100% | 100% | 0
| 8.13 | Lavatório de mãos de louça branco com coluna e sifão | un | 7 | 246.4335 | 1725.0345 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 7 | 1725.0345 | 100% | 7 | 1725.0345 | 100% | 100% | 0
| 8.14 | Torneira de lavatório metálica cromada - com fechamento automático | un | 7 | 304.84 | 2133.88 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 7 | 2133.88 | 100% | 7 | 2133.88 | 100% | 100% | 0
| 8.15 | Torneira de pia metálica para cozinha | un | 4 | 218.56 | 874.24 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 4 | 874.24 | 100% | 4 | 874.24 | 100% | 100% | 0
| 8.16 | Cuba em aço inox | un | 8 | 281.12 | 2248.96 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 8 | 2248.96 | 100% | 8 | 2248.96 | 100% | 100% | 0
| 8.17 | Instalação de esgoto completa, com tubos, conexões e acessórios | un | 27 | 82.6505 | 2231.5635 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 27 | 2231.5635 | 100% | 27 | 2231.5635 | 100% |  | 0 | 0% | 27 | 2231.5635 | 100% |  | 0 | 0% | 27 | 2231.5635 | 100% | 100% | 0
| 8.18 | Fossa séptica conforme norma - NBR 7229 | m³ | 2.26 | 526.61 | 1190.1386 |  | 0 | 0% |  | 0 | 0% | 2.26 | 1190.1386 | 100% | 2.26 | 1190.1386 | 100% |  | 0 | 0% | 2.26 | 1190.1386 | 100% |  | 0 | 0% | 2.26 | 1190.1386 | 100% |  | 0 | 0% | 2.26 | 1190.1386 | 100% | 100% | 0
| 8.19 | Filtro anaeróbio conforme norma - NBR 13969 | m³ | 1.59 | 558.98 | 888.7782 |  | 0 | 0% |  | 0 | 0% | 1.59 | 888.7782 | 100% | 1.59 | 888.7782 | 100% |  | 0 | 0% | 1.59 | 888.7782 | 100% |  | 0 | 0% | 1.59 | 888.7782 | 100% |  | 0 | 0% | 1.59 | 888.7782 | 100% | 100% | 0
| 8.20 | Caixa de passagem c/ inspeção 40x40x40cm | un | 9 | 68.08 | 612.72 |  | 0 | 0% |  | 0 | 0% | 9 | 612.72 | 100% | 9 | 612.72 | 100% |  | 0 | 0% | 9 | 612.72 | 100% |  | 0 | 0% | 9 | 612.72 | 100% |  | 0 | 0% | 9 | 612.72 | 100% | 100% | 0
| 8.21 | Caixa de gordura 60x60x60 | un | 3 | 168.59 | 505.77 |  | 0 | 0% |  | 0 | 0% | 3 | 505.77 | 100% | 3 | 505.77 | 100% |  | 0 | 0% | 3 | 505.77 | 100% |  | 0 | 0% | 3 | 505.77 | 100% |  | 0 | 0% | 3 | 505.77 | 100% | 100% | 0
| 8.22 | Reservatório de fibra capacidade 500 litros | un | 1 | 384.7325 | 384.7325 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 384.7325 | 100% | 1 | 384.7325 | 100% |  | 0 | 0% | 1 | 384.7325 | 100% | 100% | 0
INSTALAÇÕES HIDRO-SANITÁRIAS | [5 empty] | 20214.2373 |  | 0 | 0% |  | 0 | 0% |  | 3197.4068 | 15.82% |  |  |  |  | 5161.3725 | 25.53% |  |  |  |  | 384.7325 | 1.903% |  |  |  |  | 11470.7255 | 56.75% |  |  |  |  | 0
0
| 9.1 | Caixa para medidor trifásico (Medidor Eletrônico) | pç | 1 | 187.7145 | 187.7145 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 187.7145 | 100% | 1 | 187.7145 | 100% |  | 0 | 0% | 1 | 187.7145 | 100% | 100% | 0
| 9.2 | Disjuntor termomagnético monofásico 10A | pç | 10 | 9.66 | 96.6 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 10 | 96.6 | 100% | 10 | 96.6 | 100% |  | 0 | 0% | 10 | 96.6 | 100% | 100% | 0
| 9.3 | Disjuntor termomagnético monofásico 40A | pç | 1 | 54.855 | 54.855 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 54.855 | 100% | 1 | 54.855 | 100% |  | 0 | 0% | 1 | 54.855 | 100% | 100% | 0
| 9.4 | Instações elétricas - incluindo eletrodutos, conexões, fios, cabos e caixas- diversas bitolas | un. | 65 | 103.201 | 6708.065 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 65 | 6708.065 | 100% | 65 | 6708.065 | 100% |  | 0 | 0% | 65 | 6708.065 | 100% |  | 0 | 0% | 65 | 6708.065 | 100% | 100% | 0
| 9.5 | Quadro de embutir para 12 disjuntores monofásicos | pç | 1 | 102.2465 | 102.2465 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 102.2465 | 100% | 1 | 102.2465 | 100% |  | 0 | 0% | 1 | 102.2465 | 100% |  | 0 | 0% | 1 | 102.2465 | 100% | 100% | 0
| 9.6 | Luminária de sobrepor para 2 lâmpadas flour. 20W, completa | pç | 16 | 76.0955 | 1217.528 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 16 | 1217.528 | 100% | 16 | 1217.528 | 100% | 100% | 0
| 9.7 | Luminária de sobrepor para 2 lâmpadas flour. 40W, completa | pç | 17 | 82.363 | 1400.171 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 17 | 1400.171 | 100% | 17 | 1400.171 | 100% | 100% | 0
| 9.8 | Luminária tipo projetor - lampada vapor metálico 250W | pç | 4 | 120.313 | 481.252 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 4 | 481.252 | 100% | 4 | 481.252 | 100% | 100% | 0
| 9.9 | Tomada de embutir 2P+T (eletrodutos, e caixas) | pç | 20 | 70.1845 | 1403.69 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 20 | 1403.69 | 100% | 20 | 1403.69 | 100% | 100% | 0
| 9.10 | Interruptor de embutir simples - 01 seção | pç | 16 | 8.7515 | 140.024 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 16 | 140.024 | 100% | 16 | 140.024 | 100% | 100% | 0
| 9.11 | Interruptor de embutir simples - 02 seções | pç | 6 | 11.753 | 70.518 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 6 | 70.518 | 100% | 6 | 70.518 | 100% | 100% | 0
| 9.12 | Interruptor de embutir simples - 03 seções | pç | 2 | 11.753 | 23.506 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 2 | 23.506 | 100% | 2 | 23.506 | 100% | 100% | 0
| 9.13 | Interruptor de embutir simples - 01 seção - paralelo | pç | 2 | 11.753 | 23.506 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 2 | 23.506 | 100% | 2 | 23.506 | 100% | 100% | 0
| 9.14 | Interruptor de embutir simples - 02 seções - paralelo | pç | 2 | 11.753 | 23.506 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 2 | 23.506 | 100% | 2 | 23.506 | 100% | 100% | 0
| 9.15 | Entrada de energia trifásica, completa com poste, amarração, isolador, fios | un. | 1 | 823.56 | 823.56 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 823.56 | 100% | 1 | 823.56 | 100% |  | 0 | 0% | 1 | 823.56 | 100% | 100% | 0
| 9.16 | Tampa de Ferro Fundido p/caixa subterrânea 71x47cm | pç | 1 | 174.8115 | 174.8115 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 174.8115 | 100% | 1 | 174.8115 | 100% |  | 0 | 0% | 1 | 174.8115 | 100% | 100% | 0
INSTALAÇÕES ELÉTRICAS | [5 empty] | 12931.5535 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 6810.3115 | 52.66% | 0 | 6810.3115 | 52.66% |  | 1337.541 | 10.34% | 0 | 8147.8525 | 63.01% |  | 4783.701 | 36.99% | 0 | 12931.5535 | 100% | 100% | 0
| 10.1 | Lastro de brita nº. 1 - piso | m³ | 10.62 | 107.111 | 1137.5188 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 10.62 | 1137.5188 | 100% | 10.62 | 1137.5188 | 100% |  | 0 | 0% | 10.62 | 1137.5188 | 100% | 100% | 0
| 10.2 | Lona plástica preta (piso) | m² | 212.25 | 3.266 | 693.2085 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 212.25 | 693.2085 | 100% | 212.25 | 693.2085 | 100% |  | 0 | 0% | 212.25 | 693.2085 | 100% | 100% | 0
| 10.3 | Piso concreto 6cm | m³ | 12.74 | 286.281 | 3647.2199 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 12.74 | 3647.2199 | 100% | 12.74 | 3647.2199 | 100% |  | 0 | 0% | 12.74 | 3647.2199 | 100% | 100% | 0
| 10.4 | Contrapiso para bases coladas | m² | 154.71 | 20.4815 | 3168.6929 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 154.71 | 3168.6929 | 100% | 154.71 | 3168.6929 | 100% | 100% | 0
| 10.5 | Pavim.ceramica 43x43 antiderrapante PEI-4 colada | m² | 154.71 | 24.564 | 3800.2964 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 154.71 | 3800.2964 | 100% | 154.71 | 3800.2964 | 100% | 100% | 0
| 10.6 | Rodapé de cerâmica 7 cm de altura c/ argamassa colante | m | 55.43 | 9.0505 | 501.6692 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 55.43 | 501.6692 | 100% | 55.43 | 501.6692 | 100% | 100% | 0
PISOS E PAVIMENTAÇÕES | [5 empty] | 12948.6058 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 5477.9473 | 42.31% |  |  |  |  | 7470.6585 | 57.69% |  |  |  |  | 0
0
| 11.1 | Janela de vidro - J1- correr (3,00 x 0,60m) - c/ ferragens | m² | 9 | 128.478 | 1156.302 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 9 | 1156.302 | 100% | 9 | 1156.302 | 100% |  | 0 | 0% | 9 | 1156.302 | 100% | 100% | 0
| 11.2 | Janela de vidro - J2- maxim-ar (0,80 x 0,60m) - c/ ferragens | m² | 1.92 | 128.478 | 246.6778 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1.92 | 246.6778 | 100% | 1.92 | 246.6778 | 100% |  | 0 | 0% | 1.92 | 246.6778 | 100% | 100% | 0
| 11.3 | Porta/Janela de vidro temperado 10mm - PJ1- correr 4fls. (4,00 x 2,50m) - c/ ferragens | m² | 20 | 230.5 | 4610 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 20 | 4610 | 100% | 20 | 4610 | 100% |  | 0 | 0% | 20 | 4610 | 100% | 100% | 0
| 11.4 | Porta de alumínio - P1 - veneziana abrir (0,80x2,10m) - c/ ferragens | m² | 13.44 | 442.7845 | 5951.0237 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 13.44 | 5951.0237 | 100% | 13.44 | 5951.0237 | 100% |  | 0 | 0% | 13.44 | 5951.0237 | 100% | 100% | 0
| 11.5 | Porta de alumínio - P2 - veneziana abrir (0,70x2,10m) - c/ ferragens | m² | 2.94 | 442.7845 | 1301.7864 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 2.94 | 1301.7864 | 100% | 2.94 | 1301.7864 | 100% |  | 0 | 0% | 2.94 | 1301.7864 | 100% | 100% | 0
| 11.6 | Porta de alumínio - P3 - veneziana abrir (0,90x2,10m) - c/ ferragens | m² | 1.89 | 442.7845 | 836.8627 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1.89 | 836.8627 | 100% | 1.89 | 836.8627 | 100% |  | 0 | 0% | 1.89 | 836.8627 | 100% | 100% | 0
ESQUADRIAS E FERRAGENS | [5 empty] | 14102.6526 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 14102.6526 | 100% |  |  |  |  | 0 | 0% |  |  |  |  | 0
0
| 12.1 | Selador sobre alvenaria | m² | 556.19 | 4.2435 | 2360.1923 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 556.19 | 2360.1923 | 100% | 556.19 | 2360.1923 | 100% | 100% | 0
| 12.2 | Pintura em alvenaria com tinta acrílica 2 demãos - interna e externa c/ textura | m² | 476.54 | 14.26 | 6795.4604 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 476.54 | 6795.4604 | 100% | 476.54 | 6795.4604 | 100% | 100% | 0
PINTURA | [5 empty] | 9155.6527 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 9155.6527 | 100% |  |  |  |  | 0
0
| 13.1 | Soleiras e peitoris em granito | m | 24 | 61.203 | 1468.872 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 24 | 1468.872 | 100% | 24 | 1468.872 | 100% |  | 0 | 0% | 24 | 1468.872 | 100% | 100% | 0
| 13.2 | Tela de proteção contra vetores | m² | 3.6 | 150 | 540 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 3.6 | 540 | 100% | 3.6 | 540 | 100% | 100% | 0
| 13.3 | Bancada em granito | m | 9.53 | 206.0915 | 1964.052 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 9.53 | 1964.052 | 100% | 9.53 | 1964.052 | 100% | 100% | 0
| 13.4 | Tubulação em cobre | m | 18 | 17.549 | 315.882 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 18 | 315.882 | 100% | 18 | 315.882 | 100% | 100% | 0
| 13.5 | Central de Gás | un | 1 | 750 | 750 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 750 | 100% | 1 | 750 | 100% | 100% | 0
| 13.6 | Conjunto de 3 barras de apoio metálicas cromadas p/ BWC PNE | cj | 1 | 332.4 | 332.4 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 332.4 | 100% | 1 | 332.4 | 100% | 100% | 0
| 13.7 | Pergolado em madeira - impermeabilizado | m³ | 1.43 | 4850 | 6935.5 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1.43 | 6935.5 | 100% | 1.43 | 6935.5 | 100% |  | 0 | 0% | 1.43 | 6935.5 | 100% | 100% | 0
COMPLEMENTOS | [5 empty] | 12306.706 |  | 0 | 0% |  |  | 0% |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 8404.372 | 68.29% |  |  |  |  | 3902.334 | 31.71% |  |  |  |  | 0
0
| 14.1 | Extintor PQS - 6kg - com placas indicativas e instalado conforme normas | un | 1 | 107.7665 | 107.7665 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 1 | 107.7665 | 100% | 1 | 107.7665 | 100% | 100% | 0
| 14.2 | Luminária de emergência - fluorescente com inscrição "SAÍDA" - Tipo A | un | 2 | 202.06 | 404.12 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 2 | 404.12 | 100% | 2 | 404.12 | 100% | 100% | 0
| 14.3 | Luminária de emergência - fluorescente com inscrição "SAÍDA" - Tipo B | un | 2 | 202.06 | 404.12 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 2 | 404.12 | 100% | 2 | 404.12 | 100% | 100% | 0
PREVENTIVO CONTRA INCÊNDIO | [5 empty] | 916.0065 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 916.0065 | 100% |  |  |  |  | 0
0
| 15.1 | Retirada de entulhos e limpeza final da obra | m² | 171.5 | 1.2995 | 222.8642 |  | 0 | 0% |  | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% |  | 0 | 0% | 0 | 0 | 0% | 171.5 | 222.8642 | 100% | 171.5 | 222.8642 | 100% | 100% | 0
SERVIÇOS FINAIS | [5 empty] | 222.8642 |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  |  | 0 | 0% |  |  |  | 171.5 | 222.8642 | 100% |  |  |  |  | 0
TOTAL | [5 empty] | 229743.0587 |  | 29310.3239 |  |  | 29310.3239 |  |  | 37902.1649 |  |  | 67212.4888 |  |  | 63740.6326 |  |  | 130953.1213 |  |  | 41627.4535 |  |  | 172580.5748 |  |  | 57162.4839 |  |  | 229743.0587
[7 empty] | PERÍODO |  |  | ACUMULADO |  |  | PERÍODO |  |  | ACUMULADO |  |  | PERÍODO |  |  | ACUMULADO |  |  | PERÍODO |  |  | ACUMULADO |  |  | PERÍODO |  |  | ACUMULADO

## Plan1
PREFEITURA MUNICIPAL DE SÃO CRISTÓVÃO DO SUL - SC
PROJETO: CLUBE DE EVENTOS - PARTE 01
ÁREA: |  | 171.5
DATA: |  | 22/04/2012 |  |  |  |  | CRONOGRAMA FÍSICO FINANCEIRO
[5 empty] | VALOR | VALOR | 1º MÊS |  | 2º MÊS |  | 3º MÊS |  | 4º MÊS |  | 5º MÊS |  | 6º MÊS
ÍTEM |  | DESCRIÇÃO | UN | QTDADE | UNIT s/ BDI | TOTAL | % | VALOR | % | VALOR | % | VALOR | % | VALOR | % | VALOR | % | VALOR
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
#REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 2.1 | Escavação mecânica de solo prof até 1,50 m | m³ | 53.04 | 4.01 | 244.594 | 100 | 244.594 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 2.3 | Lastro de concreto magro | m³ | 0.9 | 248.94 | 257.6529 | 100 | 257.6529 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 2.4 | Sapatas de concreto armado fck 25 Mpa | m³ | 5.39 | 1173.91 | 7276.4811 | 100 | 7276.4811 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 2.5 | Colarinhos de concreto armado fck 25 Mpa c/ caixaria e escoramento | m³ | 1.84 | 1173.91 | 2483.9936 | 100 | 2483.9936 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 2.6 | Reaterro de fundações | m³ | 30.44 | 21.58 | 755.4295 | 100 | 755.4295 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| 2.7 | Vigas de baldrame de concreto armado fck 25Mpa c/ caixaria e escoramento | m³ | 7.23 | 1173.91 | 9760.4747 | 100 | 9760.4747 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| 2.8 | Impermeabilização de baldrames - 2 demãos | m² | 72.35 | 5.76 | 479.2464 | 100 | 479.2464 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
INFRA ESTRUTURA | [5 empty] | 21676.8799 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 3.1 | Pilares de concreto armado fck 25 Mpa com caixaria e escoramento | m³ | 3.78 | 1173.91 | 5102.9868 |  | 0 | 100 | 5102.9868 |  | 0 |  | 0 |  | 0 |  | 0
| 3.2 | Vigas de concreto armado fck 25 Mpa com caixaria e escoramento | m³ | 7.23 | 1173.91 | 9760.4747 |  | 0 | 100 | 9760.4747 |  | 0 |  | 0 |  | 0 |  | 0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF!
| 3.4 | Laje pré-fabricada cobertura cx d'água - esp.=12cm | m² | 14.01 | 49.88 | 803.6416 |  | 0 |  | 0 | 100 | 803.6416 |  | 0 |  | 0 |  | 0
SUPERESTRUTURA | [5 empty] | 17394.0948 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 4.1 | Alvenaria de tijolos 6 furos (10x15x20) | m² | 512.94 | 38.48 | 22698.6209 |  | 0 | 30 | 6809.5863 | 70 | 15889.0346 |  | 0 |  | 0 |  | 0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| 4.3 | Vergas e contravergas de concreto armado | m³ | 1.1 | 965.61 | 1221.4967 |  | 0 |  | 0 | 100 | 1221.4967 |  | 0 |  | 0 |  | 0
| 4.4 | Cintas em concreto armado - platibanda | m³ | 0.42 | 965.61 | 466.3896 |  | 0 |  | 0 | 100 | 466.3896 |  | 0 |  | 0 |  | 0
PAREDES E PAINÉIS | [5 empty] | 33634.3536 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 5.1 | Estrutura de madeira para cobertura fibrocimento 6mm | m² | 157.49 | 42.91 | 7771.5803 |  | 0 |  | 0 | 100 | 7771.5803 |  | 0 |  | 0 |  | 0
| 5.3 | Cobertura telha fibrocimento - 6mm | m² | 157.49 | 20.8 | 3767.1608 |  | 0 |  | 0 | 100 | 3767.1608 |  | 0 |  | 0 |  | 0
| 5.4 | Calhas galvanizadas - n°. 24 desenvolvimento 33 | m | 38.9 | 21.37 | 955.9869 |  | 0 |  | 0 |  | 0 | 100 | 955.9869 |  | 0 |  | 0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| 5.7 | Condutor PVC - 100 mm - incl. Conexões e fixadores | m | 36 | 14.37 | 594.918 |  | 0 |  | 0 |  | 0 | 100 | 594.918 |  | 0 |  | 0
COBERTURA | [5 empty] | 26381.0415 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 6.1 | Chapisco | m² | 1065.88 | 3.44 | 4216.6213 |  | 0 |  | 0 | 80 | 3373.297 | 20 | 843.3243 |  | 0 |  | 0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| 6.3 | Reboco | m² | 150.96 | 10.48 | 1819.3699 |  | 0 |  | 0 |  | 0 | 100 | 1819.3699 |  | 0 |  | 0
| 6.4 | Azulejos comuns 43x43cm PEI-4 | m² | 452.24 | 20.24 | 10526.3382 |  | 0 |  | 0 |  | 0 | 50 | 5263.1691 | 50 | 5263.1691 |  | 0
REVESTIMENTO DE PAREDES | [5 empty] | 34887.4713 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 7.1 | Forro PVC em placas com largura de 10cm esp. 8mm comp. 6m c/ tarugamento | m² | 154.71 | 30 | 5337.495 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 5337.495
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
FORROS | [5 empty] | 5337.495 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| 8.1 | Instalação de água fria completa, com tubos, conexões e acessórios | pt | 27 | 57.02 | 1770.471 |  | 0 |  | 0 | 60 | 1062.2826 | 40 | 708.1884 |  | 0 |  | 0
| 8.6 | Valvula para vaso sanitário - completa base e acabamento | un | 8 | 151.9 | 1397.48 |  | 0 |  | 0 |  | 0 | 100 | 1397.48 |  | 0 |  | 0
| 8.7 | Assento plástico para vaso sanitário s/ abertura frontal | un | 8 | 14.06 | 129.352 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 129.352
| 8.8 | Vaso sanitário | un | 8 | 141.02 | 1297.384 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 1297.384 |  | 0
| 8.10 | Porta papel higiênico | un | 8 | 37.46 | 299.68 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 299.68
| 8.11 | Porta papel toalha | un | 7 | 79.45 | 556.15 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 556.15
| 8.12 | Porta sabonete líquido | un | 7 | 22.85 | 183.9425 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 183.9425
| 8.14 | Torneira de lavatório metálica cromada - com fechamento automático | un | 7 | 304.84 | 2133.88 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 2133.88
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 60 | #REF! | 40 | #REF! |  | #REF! |  | #REF!
| 8.18 | Fossa séptica conforme norma - NBR 7229 | m³ | 2.26 | 526.61 | 1190.1386 |  | 0 |  | 0 |  | 0 | 100 | 1190.1386 |  | 0 |  | 0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 260 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| 8.22 | Reservatório de fibra capacidade 500 litros | un | 1 | 334.55 | 384.7325 |  | 0 |  | 0 | 100 | 384.7325 |  | 0 |  | 0 |  | 0
INSTALAÇÕES HIDRO-SANITÁRIAS | [5 empty] | 20214.2373 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
#REF! | [5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 10.1 | Lastro de brita nº. 1 - piso | m³ | 10.62 | 93.14 | 1137.5188 |  | 0 |  | 0 | 60 | 682.5113 | 40 | 455.0075 |  | 0 |  | 0
| 10.2 | Lona plástica preta (piso) | m² | 212.25 | 2.84 | 693.2085 |  | 0 |  | 0 |  | 0 | 100 | 693.2085 |  | 0 |  | 0
| 10.3 | Piso concreto 6cm | m³ | 12.74 | 248.94 | 3647.2199 |  | 0 |  | 0 |  | 0 | 100 | 3647.2199 |  | 0 |  | 0
| 10.4 | Contrapiso para bases coladas | m² | 154.71 | 17.81 | 3168.6929 |  | 0 |  | 0 |  | 0 | 100 | 3168.6929 |  | 0 |  | 0
| 10.5 | Pavim.ceramica 43x43 antiderrapante PEI-4 colada | m² | 154.71 | 21.36 | 3800.2964 |  | 0 |  | 0 |  | 0 | 40 | 1520.1186 | 60 | 2280.1779 |  | 0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| 10.6 | Rodapé de cerâmica 7 cm de altura c/ argamassa colante | m | 55.43 | 7.87 | 501.6692 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 501.6692 |  | 0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 50 | #REF! | 50 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
PISOS E PAVIMENTAÇÕES | [5 empty] | 12948.6058 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 11.2 | Janela de vidro - J2- maxim-ar (0,80 x 0,60m) - c/ ferragens | m² | 1.92 | 111.72 | 246.6778 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | 49.3356 | 80 | 197.3422
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
ESQUADRIAS E FERRAGENS | [5 empty] | 14102.6526 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 12.1 | Selador sobre alvenaria | m² | 556.19 | 3.69 | 2360.1923 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 2360.1923 |  | 0
| 12.2 | Pintura em alvenaria com tinta acrílica 2 demãos - interna e externa c/ textura | m² | 476.54 | 12.4 | 6795.4604 |  | 0 |  | 0 |  | 0 |  | 0 | 20 | 1359.0921 | 80 | 5436.3683
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 80 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
PINTURA | [5 empty] | 9155.6527 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| 13.1 | Soleiras e peitoris em granito | m | 24 | 53.22 | 1468.872 |  | 0 |  | 0 |  | 0 | 40 | 587.5488 | 60 | 881.3232 |  | 0
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 20 | #REF! | 60 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! | 20 | #REF! | 20 | #REF! | 60 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | 70 | #REF! | 30 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF! |  | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF! |  | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
COMPLEMENTOS | [5 empty] | 12306.706 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 14.1 | Extintor PQS - 6kg - com placas indicativas e instalado conforme normas | un | 1 | 93.71 | 107.7665 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 107.7665
| 14.2 | Luminária de emergência - fluorescente com inscrição "SAÍDA" - Tipo A | un | 2 | 202.06 | 404.12 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 404.12
| #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! | 100 | #REF!
PREVENTIVO CONTRA INCÊNDIO | [5 empty] | 916.0065 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 15.1 | Retirada de entulhos e limpeza final da obra | m² | 171.5 | 1.13 | 222.8642 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 100 | 222.8642
SERVIÇOS FINAIS | [5 empty] | 222.8642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 222.8642
TOTAL | [5 empty] | 229743.0587 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!